## HubSpot Website Migration Check
HubSpot Website Migration Checklist for a Seamless Transition
Phase 1: Planning and Strategy
Define Objectives | Clearly define your migration objectives. What do you aim to achieve by switching to HubSpot?
Content Auditing | Take inventory of all your existing website content, including pages, images, videos, and downloads.
URL Structure | If you don't have a suitable URL structure yet, devise a new one for your HubSpot website and ensure it’s SEO-friendly.
Phase 2: HubSpot Configuration & Development
Set Up HubSpot Account | Create a HubSpot portal and configure it either yourself or through a HubSpot partner.
Templates and Modules | Design or select templates and modules that align with your design and functionality goals.
Providing content | Ensure your website is filled with the right content.
Phase 3: SEO Optimization
Redirects | Set up redirects from old URLs to new HubSpot URLs to preserve SEO value and prevent 404 errors.
Meta Tags and Alt Text for SEO | Optimize meta tags, titles, and alt texts for search engines.
Responsiveness | Ensure your new HubSpot website is fully responsive on different devices and browsers.
Phase 4: Content Optimization
Content Review | Critically review your content and enhance it as needed to stay relevant and up-to-date. If you notice conversions are lacking on specific pages, consider giving them extra attention.
Phase 5: Testing and Quality Control
Cross-Browser Testing | Test your website on various browsers to ensure it functions well on all platforms and is user-friendly.
User Experience | Invite colleagues or friends to use your website and provide feedback on the user experience.
Accessibility | Consider web accessibility to ensure your site can be used by people with disabilities.
Phase 6: SEO Monitoring
Monitor SEO Performance | Keep an eye on your website's performance using SEO tools like HubSpot SEO Scan or Semrush. Adjust your strategy and content as needed.
Phase 7: Launch
Back-Up | Create a complete backup of your old website before switching to HubSpot.
Timing | Schedule the migration for a date and time when it will have the least impact on your visitors.
DNS Configuration | Proper DNS settings are crucial for your website's online visibility.
Phase 8: Post-Migration
Check URLs
Submit Sitemap | Send an updated XML sitemap to search engines like Google Search Console to inform them of the changes.
Set Up Analytics | Configure Google Analytics or other analytics tools to monitor your new website.

## CMS Best Practice
HubSpot CMS Developer Best Practices
1 | Theme & Module Architecture
| Use HubSpot Themes | Organize your assets using themes to maintain consistency and scalability.
| Modular Design | Develop reusable modules to promote DRY (Don't Repeat Yourself) principles.
| Theme Fields | Implement theme fields to allow content editors to customize styles without modifying code
2 | Performance Optimization/Website Speed
| Image Handling | Optimize images by using appropriate formats (e.g., WebP) and sizes. HubSpot automatically converts images to WebP and allows resizing using resize_image_url()
| Minimize HTTP Requests | Combine CSS and JavaScript files where possible.
| Lazy Loading | Implement lazy loading for images and videos to enhance page load times.
| Code Split | Leverage HubSpot Modules and Template system to code split
Use a boilerplate, don’t start from scratch every time.
3 | Accessibility Compliance
| Semantic HTML | Use proper HTML tags to convey meaning and structure.
| Keyboard Navigation | Ensure all interactive elements are accessible via keyboard.
Use semantic markup
Image alt text
4 | Build for the content creator | Build a system not an individual web page
5 | SEO Best Practices
| Meta Tags | Include relevant meta titles and descriptions for each page.
| Structured Data | Implement schema markup to enhance search engine understanding.
| Clean URLs | Maintain readable and keyword-rich URLs.
6 | Security Measures
| Input Validation | Sanitize and validate all user inputs to prevent XSS and SQL injection attacks.
| HTTPS | Ensure all pages are served over HTTPS to secure data transmission.
| Regular Updates | Keep all dependencies and modules up to date to patch known vulnerabilities.
7 | Content Migration
| Content Audit: | Assess existing content for relevance and quality before migration.
| URL Mapping | Create a URL mapping strategy to maintain SEO rankings.
| Redirects | Implement 301 redirects for any changed URLs to preserve link equity.
8 | Version Control & Deployment
| CMS CLI | Utilize HubSpot's CMS CLI for local development and deployment.
| Git Integration | Integrate with Git for version control to track changes and collaborate effectively.
| Staging Environment | Test changes in a staging environment before deploying to production.

## Security_Validations
Feature | Purpose | HubSpot Default Support | Testing Approach
Validation of Components and Templates | Ensure custom modules, templates, and global content work as expected. | No | Manual + Preview
Accessibility Testing | Ensure your site is usable for people with disabilities. | Partial | Use browser tools (Lighthouse, axe)
CMS Page Validation (Post-Migration) | Ensure all migrated pages (from AEM/WordPress) are correctly rendered and functional. | No | QA checklist, crawlers
Security Testing for Component Code | Ensure custom modules/templates are not vulnerable. | Partial | Static analysis + secure coding | We can use require_js,get_asset_url,require_css and HubL's built-in filters (like default and to_string) to sanitize and format data as needed.
User Acceptance Testing (UAT) Case Preparation | Let stakeholders review and approve functionality. | No | Manual test case creation